## To-do list
Beyond the Bench Summit - Task List
10-14 WEEKS BEFORE EVENT
Task | Due Date | Assigned to | Status | Notes
Research venues |  |  |  | Room size, set up, parking, A/V equipment
Draft Save the Date
Assemble invite list
Assemble Planning Committee
6-10 WEEKS BEFORE EVENT
Task | Due Date | Assigned to | Status | Notes
Draft Fact Pattern
Planning Committee - 1st meeting
Finalize contract with venue
Save the Date sent - Groups A, B & C
Draft invitation language
Secure event security
Finalize press plan
Create RSVP link
Create event landing page
2-5 WEEKS BEFORE EVENT
Task | Due Date | Assigned to | Status | Notes
Planning Committee - 2nd & 3rd meetings
Send invite - Groups 1, 2 & 3
Inquire about hotel courtesy block
Finalize speakers & event agenda
Draft event brochure
Finalize fact pattern
Draft op ed
Schedule conference calls with all speakers
1 WEEK BEFORE EVENT
Task | Due Date | Assigned to | Status | Notes
Send event reminder
Finalize brochure and sent to printer
Create event signage
Request speaker bios
Op editorial sent to newspapers
Request speaker notes
Draft post event evaluation survey
Finalize video montage
Finalize catering |  |  |  | Coffee service, lunch, refreshments/break
2 DAYS BEFORE EVENT
Task | Due Date | Assigned to | Status | Notes
Send press release to media
Confirm all speakers
Confirm IT/AV needs
Send event reminder to event participants
Confirm security
Finalize breakout groups + facilitators
1 DAY BEFORE EVENT
Task | Due Date | Assigned to | Status | Notes
Bring timing cards, index cards for breakouts
Set up venue |  |  |  | Auditorium for am; tables for lunch and breakouts, green room for speakers
Consider special seating needs (i.e. media, security)
Small group meeting to cover event details
Test A/V equipment
Bring meeting materials |  |  |  | Timing cards for speakers, index cards for breakouts, table tents for afternoon panel, name badges
DAY OF EVENT
Task | Due Date | Assigned to | Status | Notes
Breakout group facilitator training 9am
MONTH AFTER EVENT
Task | Due Date | Assigned to | Status | Notes
Send Thank You notes
Distribute post event survey
Gather breakout session activity responses
Evaluate survey results